## Slide 1
HelixTriage — Pilot Rollout Plan
AI-assisted ticket triage for the enterprise service desk
System: HelixTriage · Reference: RAI-RD-20260415-helixtriage · Owner: Enterprise Service Management

## Slide 2
Why we are piloting
HelixTriage pilot · objectives
• 41% of tickets are misrouted on first assignment today
• Each misroute adds an average of 6.4 hours to resolution
• Ticket volume up 23% year on year with flat headcount
• HelixTriage predicts resolver group and priority, and drafts a first response

## Slide 3
What the pilot covers
HelixTriage pilot · scope
• Two resolver groups: Network & Connectivity, Identity & Access
• Approximately 1,200 tickets per week from the pilot cohort
• Predictions served from the internal endpoint helixtriage-inference.svc.internal.corp
• Every prediction reviewed by an agent — no autonomous resolution
• Tickets flagged as containing personal data are excluded at intake

## Slide 4
Timeline
HelixTriage pilot · eight weeks
• Weeks 1–2 — shadow mode: predictions logged but hidden from agents
• Weeks 3–6 — assisted mode: predictions shown as suggestions
• Week 7 — evaluation checkpoint against the held-out dataset
• Week 8 — go / no-go decision for wider rollout

## Slide 5
Success criteria
HelixTriage pilot · exit gates
• First-assignment accuracy above 85% (evaluation result: 87.1%)
• Misroute rate below 15% in the cohort (evaluation result: 12.8%)
• Agent acceptance of suggested responses above 60% (result: 63.4%)
• No increase in reopened-ticket rate against the manual baseline

## Slide 6
Risks and mitigations
HelixTriage pilot · risk register
• Agent over-reliance — suggestions marked as AI-generated, explicit acceptance required
• Taxonomy drift — weekly sampling of 50 overridden predictions
• Latency under peak load — 4-second timeout falls back to manual triage
• Personal data exposure — intake exclusion plus signature stripping

## Slide 7
Governance and next steps
HelixTriage pilot · governance
• HelixTriage registered under reference RAI-RD-20260415-helixtriage
• Model, prompt and taxonomy versions logged against every prediction
• Predictions retained for 90 days for audit
• Monthly review of the confidence threshold against override rate
• Related documents: requirements, solution design, evaluation results, evaluation dataset